## Overview
BS-V1
Item | Test Description | Board Status |  | Comments
|  | 1 | 2 |  | Key
Visual Inspection | Look over the boards for anything out of place |  |  | Lot of flux left over, bad silk, components weak/lifted; D1/D7 fell off |  | Not Started
Diode Polarity | Test diode continuity with meter |  |  |  |  | In Progress
Rail > GND Shorts | Use chart to check impedances for shorts |  |  |  |  | Complete
Rail > Rail Shorts | Use chart to check impedances for shorts |  |  |  |  | Issue
Power On + Power LED | "Smoke test" with battery
Voltages and Sequencing | Verify voltages of all rails and record | FIXED | FIXED | Remove D4, Q1 and short DS
Button LED | Press button and confirm blue LED illuminates | FIXED | FIXED | Remove R3, Replace R4 = 47ohm, Cut SW1.3-4, Wire SW1.3 to SW1.6
USB Charging | Connect USB-C, verify charge current with meter to battery, charge LED on
LDO Input Selection | Connect battery only, battery + USB and confirm FET voltage with meter |  |  | Replace in next version (see above)
Programming Connector | Load test firmware using programmer and Tag Connect, verify LEDs flash
USB TTL Bridge + Autoreset | Load test firmware via Arduino IDE, verify LEDs flash
Button Press + User LEDs | Use test firmware to confirm button press turns on user LED, other LED runs as heartbeat
BLE | Load test BLE firmware and verify connection with phone
DFU Header | TBD

## Polarity
Diode | (-) Terminal | Board Status
|  | 1 | 2
D1 | N/A |  |  | Knocked D1 off
D2 | R5
D3 | 3.3V
D4 | Q1
D5 | GND
D6 | GND
D7 | N/A
D8 | VBUS_IN
SW1 | GND

## Rail > GND
Rail | Probe Point | Resistance to DGND (Ω)
|  | 1 | 2
VIO | C4.2
VIN_LDO | C10.2
VBUS_IN | L1.1
VBUS | L1.2
VBAT | J3.2
3V3 | C12.2

## Rail > Rail
Rail/Rail | VIO | VIN_LDO | VBUS_IN | VBUS | VBAT | 3V3
VIO |  | 2X | 2X | 2X | 2X | 2X
VIN_LDO |  |  | 2X | 2X | 2X | 2X
VBUS_IN |  |  |  | 2X | 2X | 2X | Shorted
VBUS |  |  |  |  | 2X | 2X
VBAT | [5 empty] | 2X
3V3
[8 empty] | VIO | C4.2
[8 empty] | VIN_LDO | C10.2
[8 empty] | VBUS_IN | L1.1
[8 empty] | VBUS | L1.2
[8 empty] | VBAT | J3.2
[8 empty] | 3V3 | C12.2

## Voltages
Rail | Probe Point | Voltage (V)
|  | 1 | 2
VIO | C4.2 | 3.42V | 3.40V
VIN_LDO | C10.2 | 4.14V | 4.10V
VBUS_IN | L1.1 | 4.80V | 5.00V
VBUS | L1.2 | 4.575V | 4.95V
VBAT | J3.2 | 4.14V | 4.10V
3V3 | C12.2 | 2.67V | 3.33V